## Tabelle1
1	Data Communication	0
2	Distributed data processing	0
3	Performance	1			Input	5	x3	=	15
4	Heavily used configuration	0			Output	8	x4	=	32
5	Transaction rate	0			Query	6	x3	=	18
6	Online data entry	0
7	End user efficiency	0					ct	65
8	Online update	0
9	Complex processing	0
10	Reusability	1
11	Installation ease	0
12	Operational ease	5
13	Multiple sites	3
14	Facilitate change	0

	Fi	10
							E=6	KLOC	2,393
	Java	53
							D=1
				FP=ct*(0,65+0,01xFi)			COCOMO
							Effort applied(	in person-month)			6=E/1
				Fp=48			Organic
				LOC=48x53					E=a*L^b	2,4*2,544^1,05	6,4		E=12	KLOC	4,63
				LOC=2544		a	2,4
				KLOC=2,544		b	1,05		D=c*E^d	2,5*6,4^0,38	5,06		D=2
						c	2,5
						d	0,38		P=E/D	6,4/5,06	1,26		6=E/2